## Sheet1
ANNUAL PLAYGROUND INSPECTION WORK REPORT 2025
SITE | RISK | RECOMMENDATION | ACTION
QUEENS ROAD
Seats/benches need adjusting | LOW | Adjust | Checked. Monitor for now
Both Seesaw side bolts feel loose | MED | Adjust | No change since installation
Flat swing bushes wearing | LOW | Monitor | Monitor
BMx track tarmac chunks taken out in places | MED | Repair | Repairs required by contractor
CALDY VALLEY
Hand fence by steps from car park loose | HIGH | Repair | Extra posts now installed
Caps missing on Toddler zone- finger trap | HIGH | Replace | New caps now fitted
VAUGHANS LANE
Access gate spring missing | HIGH | Replace | New spring fitted
Roundabout inside bearing needs greasing | MED | Needs repairing | Unable to gain access to inspect
Climbing frame tyre unit: | HIGH | Repair | Pictured rope wrapped in self
Wire is showing through, well worn & all need to be replaced urgently |  |  | amalgamation tape; no wire
Trip hazards outside access gate |  |  | All removed
THACKERAY DRIVE
Flat swing bushes well worn | HIGH | Replace | Under investiagtion by MO
Activity trail bolts loose | HIGH | Adjust | Adjusted
Toddler multiplay steering wheel loose | HIGH | Adjust | Adjusted
Toddler multiplay bird mess | HIGH | Clean off | Cleaned off, but may return
Contractor Work:
Thackeray; Swing bushes, Maintenance Officer investigating supply of new bushes.
Vaughans - Wire between all tyres to be replaced - Need External contractor - Poplars Forge contacted to quote, & possibly ROSPA for supplier details
Roundabout at Vaughan's Lane - Maintenance Officer can not get access to grease - asking Poplars Forge, but medium risk only, can wait
Missing Patched on Josh's Jumps track - need extra surface, contractor work but medium risk at present so can wait